## Sheet1
Time box | From 1-March 2022 to 13-April 2022
User stories | 17 User stories
SPRINT 1 BACKLOG (01/03/2022 - 12/03/2022)
User Story ID | User stories | Task | Assigned to | Initial Estimate (hour) | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12
|  |  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12
1 | As a user, I want to login into the system | Front-end coding | Vy Vy | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Back-end coding | Anh Tuan | 8 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Login function testing | Quynh Tien | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | As a user, I want to post my ideas to contribute to improving the University | Front-end coding | Vy Vy | 20 | 0 | 0 | 4 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Back-end coding | Anh Tuan | 22 | 0 | 0 | 0 | 0 | 0 | 6 | 8 | 8 | 0 | 0 | 0 | 0
|  | Posting function coding | Quynh Tien | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0
3 | As a user, I want to comment on the other posts | Front-end coding | Vy Vy | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 7 | 0 | 0 | 0 | 0
|  | Back-end coding | Anh Tuan | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 6 | 0 | 0
|  | Comment function testing | Quynh Tien | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
4 | As a user, I want to thumbs up or thumbs down other ideas | Front-end coding | Vy Vy | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0
|  | Back-end coding | Anh Tuan | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0
|  | Function testing | Quynh Tien | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
5 | As a user, I want to modify my profile | Front-end coding | Vy Vy | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0
|  | Back-end coding | Anh Tuan | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
|  | Testing (reaction and modify profile | Quynh Tien | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Idea - Remaining efforts in uninterrupted working hours |  |  |  | 130 | 119.1667 | 108.3333 | 97.5 | 86.6667 | 75.8333 | 65 | 54.1667 | 43.3333 | 32.5 | 21.6667 | 10.8333 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  |  | 130 | 126 | 122 | 114 | 102 | 90 | 84 | 70 | 55 | 36 | 15 | 7 | 0
SPRINT 2 BACKLOG (13/03/2022 - 20/03/2022) | bar: 2022-03-01 to 2022-03-08
User Story ID | User stories | Task | Assigned to | Initial Estimate (hour) | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20
|  |  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8
1 | As a user, I want to post the idea as an anonymous | Front-end coding | Vy Vy | 26 | 8 | 8 | 4 | 0 | 6 | 0 | 0 | 0
|  | Back-end coding | Anh Tuan | 24 | 0 | 0 | 0 | 10 | 0 | 4 | 4 | 6
|  | Function testing | Quynh Tien | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 2
2 | As an Admin I want to create an event | Front-end coding | Vy Vy | 27 | 0 | 0 | 8 | 7 | 6 | 6 | 0 | 0
|  | Back-end coding | Anh Tuan | 22 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 4
|  | Function testing | Quynh Tien | 20 | 0 | 0 | 0 | 8 | 0 | 2 | 8 | 2
3 | As an Admin I want to close an event | Front-end coding | Vy Vy | 16 | 0 | 0 | 0 | 0 | 4 | 6 | 0 | 6
|  | Back-end coding | Anh Tuan | 18 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 6
|  | Function testing | Quynh Tien | 20 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 8
Idea - Remaining efforts in uninterrupted working hours |  |  |  | 183 | 160.125 | 137.25 | 114.375 | 91.5 | 68.625 | 45.75 | 22.875 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  |  | 183 | 175 | 167 | 155 | 130 | 108 | 72 | 34 | 0
SPRINT 3 BACKLOG (21/03/2022 - 28/03/2022)
User Story ID | User stories | Task | Assigned to | Initial Estimate (hour) | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 | 2022-03-28
|  |  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8
1 | As a QA Manager, I want to create a new category | Front-end coding | Vy Vy | 28 | 8 | 8 | 4 | 8 | 0 | 0 | 0 | 0
|  | Back-end coding | Anh Tuan | 18 | 0 | 0 | 0 | 8 | 6 | 4 | 0 | 0
|  | Function testing | Quynh Tien | 8 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0
2 | As a QA Manager, I want to download files as CSV extensions after the event closed | Front-end coding | Vy Vy | 10 | 0 | 0 | 6 | 0 | 0 | 4 | 0 | 0
|  | Back-end coding | Anh Tuan | 30 | 0 | 0 | 0 | 0 | 10 | 8 | 8 | 4
|  | Function testing | Quynh Tien | 14 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 2
3 | As an QA Coordinator, I want to receive mail when department's staff posts new idea | Front-end coding | Vy Vy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Back-end coding | Anh Tuan | 24 | 0 | 0 | 0 | 4 | 0 | 4 | 8 | 8
|  | Function testing | Quynh Tien | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8
Idea - Remaining efforts in uninterrupted working hours |  |  |  | 148 | 129.5 | 111 | 92.5 | 74 | 55.5 | 37 | 18.5 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  |  | 148 | 140 | 132 | 122 | 102 | 74 | 46 | 22 | 0
SPRINT 4 BACKLOG (29/03/2022 - 05/04/2022)
User Story ID | User stories | Task | Assigned to | Initial Estimate (hour) | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05
|  |  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8
1 | As a Admin, I want to create accounts for users | Front-end coding | Vy Vy | 23 | 8 | 6 | 4 | 4 | 0 | 0 | 1 | 0
|  | Back-end coding | Anh Tuan | 22 | 0 | 0 | 0 | 6 | 8 | 6 | 0 | 2
|  | Function testing | Quynh Tien | 13 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 1
2 | As a QA Manager, I want to delete if they have not been used. | Front-end coding | Vy Vy | 12 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0
|  | Back-end coding | Anh Tuan | 22 | 0 | 0 | 0 | 0 | 0 | 6 | 8 | 8
|  | Function testing | Quynh Tien | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2
3 | As a user, I want to use a simple website that is easy to use | Test UI | Quynh Tien | 34 | 0 | 0 | 5 | 0 | 3 | 8 | 10 | 8
Idea - Remaining efforts in uninterrupted working hours |  |  |  | 132 | 115.5 | 99 | 82.5 | 66 | 49.5 | 33 | 16.5 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  |  | 132 | 124 | 118 | 103 | 87 | 76 | 52 | 21 | 0
SPRINT 5 BACKLOG (06/04/2022 - 13/04/2022)
User Story ID | User stories | Task | Assigned to | Initial Estimate (hour) | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10 | 2022-04-11 | 2022-04-12 | 2022-04-13
|  |  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8
1 | As a user, I want to secure my information | Testing | Quynh Tien | 22 | 4 | 8 | 0 | 4 | 0 | 2 | 0 | 4
2 | As a user, I want the server to respond to me in a second | Back-end coding | Anh Tuan | 18 | 0 | 8 | 0 | 4 | 0 | 4 | 2 | 0
|  | Testing | Quynh Tien | 16 | 0 | 0 | 0 | 8 | 4 | 0 | 4 | 0
3 | As a user, I want to surf the web not only on the desktop but also on the phone and tablet | Front-end coding | Vy Vy | 22 | 8 | 6 | 0 | 0 | 0 | 6 | 0 | 2
|  | Testing | Quynh Tien | 22 | 0 | 0 | 4 | 4 | 0 | 8 | 0 | 6
Idea - Remaining efforts in uninterrupted working hours |  |  |  | 100 | 87.5 | 75 | 62.5 | 50 | 37.5 | 25 | 12.5 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  |  | 100 | 88 | 66 | 62 | 42 | 38 | 18 | 12 | 0
SPRINT BACKLOG (01/03/2022 - 13/04/2022)
User Story ID | User stories | Task | Assigned to | Initial Estimate (hour) | time axis 2022-03-01 to 2022-04-13
Day 0 | time axis 2022-03-01 to 2022-04-13
1 | As a user, I want to login into the system | Front-end coding | Vy Vy | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Back-end coding | Anh Tuan | 8 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Login function testing | Quynh Tien | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | As a user, I want to post my ideas to contribute to improving the University | Front-end coding | Vy Vy | 20 | 0 | 0 | 4 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Back-end coding | Anh Tuan | 22 | 0 | 0 | 0 | 0 | 0 | 6 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Posting function coding | Quynh Tien | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | As a user, I want to comment on the other posts | Front-end coding | Vy Vy | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Back-end coding | Anh Tuan | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Comment function testing | Quynh Tien | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | As a user, I want to thumbs up or thumbs down other ideas | Front-end coding | Vy Vy | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Back-end coding | Anh Tuan | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Function testing | Quynh Tien | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | As a user, I want to modify my profile | Front-end coding | Vy Vy | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Back-end coding | Anh Tuan | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Testing (reaction and modify profile | Quynh Tien | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | As a user, I want to post the idea as an anonymous | Front-end coding | Vy Vy | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 4 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Back-end coding | Anh Tuan | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 4 | 4 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Function testing | Quynh Tien | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | As an Admin I want to create an event | Front-end coding | Vy Vy | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 7 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Back-end coding | Anh Tuan | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Function testing | Quynh Tien | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 2 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | As an Admin I want to close an event | Front-end coding | Vy Vy | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Back-end coding | Anh Tuan | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Function testing | Quynh Tien | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | As a QA Manager, I want to create a new category | Front-end coding | Vy Vy | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Back-end coding | Anh Tuan | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Function testing | Quynh Tien | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | As a QA Manager, I want to download files as CSV extensions after the event closed | Front-end coding | Vy Vy | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Back-end coding | Anh Tuan | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Function testing | Quynh Tien | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | As an QA Coordinator, I want to receive mail when department's staff posts new idea | Front-end coding | Vy Vy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Back-end coding | Anh Tuan | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Function testing | Quynh Tien | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | As a Admin, I want to create accounts for users | Front-end coding | Vy Vy | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6 | 4 | 4 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Back-end coding | Anh Tuan | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 8 | 6 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Function testing | Quynh Tien | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | As a QA Manager, I want to delete if they have not been used. | Front-end coding | Vy Vy | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Back-end coding | Anh Tuan | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Function testing | Quynh Tien | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | As a user, I want to use a simple website that is easy to use | Test UI | Quynh Tien | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 3 | 8 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | As a user, I want to secure my information | Testing | Quynh Tien | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 0 | 4 | 0 | 2 | 0 | 4
2 | As a user, I want the server to respond to me in a second | Back-end coding | Anh Tuan | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 4 | 0 | 4 | 2 | 0
|  | Testing | Quynh Tien | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 4 | 0
3 | As a user, I want to surf the web not only on the desktop but also on the phone and tablet | Front-end coding | Vy Vy | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6 | 0 | 0 | 0 | 6 | 0 | 2
|  | Testing | Quynh Tien | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 8 | 0 | 6
Idea - Remaining efforts in uninterrupted working hours |  |  |  | 693 | 677.25 | 661.5 | 645.75 | 630 | 614.25 | 598.5 | 582.75 | 567 | 551.25 | 535.5 | 519.75 | 504 | 488.25 | 472.5 | 456.75 | 441 | 425.25 | 409.5 | 393.75 | 378 | 362.25 | 346.5 | 330.75 | 315 | 299.25 | 283.5 | 267.75 | 252 | 236.25 | 220.5 | 204.75 | 189 | 173.25 | 157.5 | 141.75 | 126 | 110.25 | 94.5 | 78.75 | 63 | 47.25 | 31.5 | 15.75 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  |  | 693 | 689 | 685 | 677 | 665 | 653 | 647 | 633 | 618 | 599 | 578 | 570 | 563 | 555 | 547 | 535 | 510 | 488 | 452 | 414 | 380 | 372 | 364 | 354 | 334 | 306 | 278 | 254 | 232 | 224 | 218 | 203 | 187 | 176 | 152 | 121 | 100 | 88 | 66 | 62 | 42 | 38 | 18 | 12 | 0